## Enda Peng
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (01/27-02/03) | 10 | 10 | 1 | 0 - learning python, git ( Creat a git account and learn basic git operations. Join our team repo.) 1 - gather requirements (Install previous project on my own machine and test it. Find bugs and where to improve) 3-implementation (Install the template VM for development, which has integrated python, django, eclipse) 5 - attend group meeting (Give my opinion on how we improve current project) | 3 | 4 |  | 2 |  | 1 |  | Continue to learn all the tool, try some sample code on django | 14
3 (02/03-02/09) | 6 | 6 | 2 | 1. analyze requirement find bugs and add it to povital tracker 0. learn how to program with python and django 5 meeting with others to discuss which part to be implemented | 2 | 2 |  |  |  | 2 |  | divide tasks and begin to fix bugs on existing system | 10
4(02/10-02/16) | 6 | 6 | 1 | 0 learn selenium 3 write test script | 4 |  |  | 2 |  |  |  |  | 6
02/17 - 02/23 | 6 | 6 | 1 | 0 - learning about Django 4 - learned unittest ，fix bugs in current test script | 2 | 0 | 0 | 4 | 0 | 0 | 0 |  | 6
02/24-3/1 | 6 | 6 | 1 | 0 - preparing for implementation locate bugs 4 search method and document to understand previous work | 2 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 6
03/2-3/8 | 6 | 6 | 1 | 3 - implement backlog function | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
03/9-3/15 | 6 | 6 | 1 | 3 - implement backlog UI | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
3/16-3/22 | 10 | 9 | 1 | 3- implement backlog backend function | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0
3/23-3/29 | 8 | 7 | 1 | 3- implement new version of backlog | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0
3/30-4/5 | 6 | 5 | 1 | 3- implement new version of backlog 4- write test for new function | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0
4/6-4/12 | 4 | 2 | 2 | 3- design new method to implement new backlog function 4- write test for new function | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
4/13-4/19 | 7 | 6 | 1 | 3- add priority | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
4/20-4/26 | 4 | 3 | 1 | 3- add priority, fix template for priority | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0

## Randy Charland
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (01/27-02/03) | 12 | 12 | 2 | 0 - learning python, git, django, previous project code 1 - Proposed enhancements/fixes for class project 3 - Implemented group GIT repository and migrated previous project code 5 - attended group meetings | 7 | 1 |  | 2 |  | 2 |  | Continue to learn tools and previous project code, work on SPPP document, attend meetings
3 (02/03-02/09) | 15 | 15 | 3 | 0 - learning django, python and existing tool 1 - Analyzed Requirement tool and added detailed stories to Pivotal Tracker 3 - Added users to collaborators to group repository and authored Config Mgt section fo SPPP 5 - Attended group meetings | 8 | 2 |  | 1 |  | 4 |  | Focus on Python and Django environment management
4 (02/10-02/16) | 7 | 7 | 2 | 0 - learning django, Eclipse and existing tool 3 - Helped users with git instantiations 5 - Attended group meetings | 4 |  |  | 1 |  | 2 |  | Focus on developing and executing Python unit testing for assigned iteration story
5 (02/17-02/23) | 12 | 12 | 3 | 0 - learning django, Python unit tests, and Selenium Tests 2 - Designed Python unit test for Requirements Tool Iteration Bug 3 - Helped users with git commit proccess, implemented Python unit test and fixed existing Selenium tests 5 - Attended group meetings, also helped several users with Python and Selenium installation and configuration | 4 |  | 1 | 4 |  | 3 |  | Focus on developing and executing Python unit testing for assigned iteration story
6 (02/24-03/01) | 11 | 11 | 2 | 0 - learned Python unit and selenium testing, merged code and git maintenance 2 - designed unit tests 3 - Implemented unit tests and fixed Selenium tests 4 - Performed testing of devteam branches 5 - Attended group meetings | 2 |  | 1 | 4 | 2 | 2 |  | Focus of fixing identified bugs and adding new functionality
7 (03/02-03/08) | 4 | 4 | 2 | 0 - learned Python and Django 2 - designed improvements to Project Detail 5 - Attended group meetings | 1 |  | 1 |  |  | 2 |  | Focus on developing improvements to Project Detail Iteration 2
8 (03/09-03/15) | 8 | 8 | 1 | 0 - learned Python and Django 3 - Implemented improvements to Project Detail 5 - Attended group meetings | 3 |  |  | 4 |  | 1 |  | Focus on developing improvements to Project Detail for Iteration 2
9 (03/16-03/22) | 13 | 13 | 2 | 0 - learned Python and Django 3 - Implemented improvements to Attachment Feature 4 - testing implemented features 5 - Attended group meetings | 2 |  |  | 8 | 1 | 2 |  | Focus on developing improvements to Project Detail for Iteration 2
10 (03/23-03/29) | 12 | 12 | 3 | 0 - learned Python and Django 3 - Implemented remaining functionality in Project Detail and Attachment Feature 4 - testing implemented features 5 - Attended group meetings | 0 |  |  | 10 | 1 | 1 |  | Focus on developing requirements for Iteration 3
11 (3/30-04/05) | 4 | 4 | 2 | 0 - learned Python and Django 1 - Determined stories for iteration 3 2 - designed improvements to Project Detail, Backlog, and Issue List 4 - testing implemented features 5 - Attended group meetings | 0 | 2 | 1 |  |  | 2 |  | Focus on implemeting requirements for Iteration 3
12 (4/5-4/12) | 13 | 13 | 1 | 0 - learned Python and Django 3 - implemented improvements with Backlog, Issue List, and Project Detail 4 - testing implemented features 5 - Attended group meetings | 0 |  |  | 10 | 2 | 1 |  | Focus on implemeting requirements for Iteration 3
13 (4/12-4/19) | 3 | 3 | 1 | 0 - learned Python and Django 3 - Optimizing Backlog and Issue List 4 - testing implemented features 5 - Attended group meetings | 0 |  |  | 1 | 1 | 1 |  | Focus on testing for Iteration 3 and final presentation
13 (4/20-4/26) | 10 | 10 | 4 | 0 - learned Python and Django 3 - Fixed bugs and worked on prioritizing stories in Backlog view 4 - testing implemented features 5 - Attended group meetings and final project preparation and staging server | 0 |  |  | 3 | 3 | 4

## Chris Willis
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
01/27 - 02/02 | 8 | 7 | 1 | 0 - Researching project management tools and experimenting with Blueprints 1 - Brainstorming features to add and improvements to make to Blueprints 3 - Creating development VM for group | 2 | 2 | 0 | 3 | 0 | 0 | 0
02/03 - 02/09 | 9 | 7 | 2 | 0 - researching other requirements management tools for my portion of the SPPP. Researching Django and reading past team's documentation 1 - sections 1, 2, and 6A for the SPPP document. Creating drafts of stories in Pivotal Tracker | 4 | 3 | 0 | 0 | 0 | 0 | 0
02/10 - 02/16 | 5 | 5 | 0 | 0 - homework 2 and learning Django and Git | 5 | 0 | 0 | 0 | 0 | 0 | 0
02/17 - 02/23 | 14 | 12 | 2 | 0 - learning about Django 4 - learned unittest and selenium and worked on implementing a test script | 3 | 0 | 0 | 0 | 9 | 0 | 0
02/24 - 03/01 | 10 | 9 | 1 | 3 - implemented test script 4 - tested new test script 5 - created PowerPoint for 03/02 iteration 1 presentation | 0 | 0 | 0 | 5 | 2 | 2 | 0
03/02 - 03/08 | 13 | 11 | 2 | 0 - working on homework 3 3 - attempted to fix the file upload bug. Last team appears to be using JS and Django to verify. I'm going to work with the team to figure out how to approach this. | 5 | 0 | 0 | 6 | 0 | 0 | 0
03/09 - 03/15 | 9 | 8 | 1 | 0 - working on homework 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0
03/16 - 03/22 | 11 | 10 | 1 | 3 - implementing storyAttachment model so that files can be attached at the story level. Integrated code with Allen's story attachment view. 0 - discussion board question | 1 | 0 | 0 | 9 | 0 | 0 | 0
03/23 - 03/29 | 8 | 8 | 0 | 3 - worked on implementing delete attachment at story level 4 - code review and understanding code implented by others | 0 | 0 | 0 | 6 | 2 | 0 | 0
03/30 - 04/05 | 9 |  | 2 | 0 - working on homework 4 3 - implementing story-level attachment features at the project level | 6 | 0 | 0 | 1 | 0 | 0 | 0
04/06 - 04/12 | 8 | 7 | 1 | 0 - working on homework 4 4 - worked on getting code coverage to work with django and implementing unit tests for the files and user_manager models | 3 | 0 | 0 | 0 | 4 | 0 | 0
04/13 - 04/19 | 12 | 12 | 0 | 3 - implemented HTTPS on the live server and attempted to create unit tests for user_manager and files models, but my I ran into issues with breakpoints in Eclipse environment and couldnt troubleshoot something which led to me eventually blowing up my Eclipse environment and trying to fix it for hours. My second day trying I was able to develop the unit tests for user_manager and files models | 0 | 0 | 0 | 12 | 0 | 0 | 0
04/20-04/26 | 5 | 4 | 1 | 5 - created my slides for the presentation and filled in parts of the test report. 3 - Randy discovered an issue with the communication tool due to ask implementation so I looked through the nginx config files and disabled redirect to ssl. | 0 | 0 | 0 | 2 | 0 | 2 | 0

## Tshudy Allen
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (01/27-02/03) | 14 | 12 | 2 | 0 - learning python, git 1 - gather requirements - review current product management tool and list 5 enhancements that could be made to the tool 5 - attend group meeting | 10 | 2 |  |  |  | 2 |  | Continue to learn all the tools, setup my own vm environment for development, work on SPPP document, attend meetings. | 14
3 (02/03-02/10) | 12 | 10 | 3 | 0 - learning python and django, setup vm environment 1 - review current product to find defects and new features 5 - atended meeting after class and a call-in meeting | 6 | 2 |  |  |  | 4 |  | Continue to learn all the tools, Pick a story from the interation and start working on it. | 12
4 (02/10-02/17) | 8 | 5 | 3 | 0 - learning python and django, setup vm environment 1 - review current story added two task 5 - atended meeting after class and a call-in meeting | 3 | 2 |  |  |  | 3 |  | Continue to learn all the tools, Looked at getting the current PyUnit and selemium test working. Having difficutly with GIT trying to checkou a branch. | 8
5 (02/17-02/24) | 12 | 11 | 1 | 0 - learning python and django 1 - Ran the selenium tests. Required modification to run successfully, need to fix some tests 3 - Implemented 3 unit tests for testing the attachment bug 5 - atended meeting after class and a call-in meeting 6 - interation planning | 4 | 1 |  | 6 |  | 1 |  | Continue to learn all the tools, I was able to run the existing PyUnit and selemium tests. I added 3 additional unit tests fir the attached bug. | 8
6 (02/24-03/02) | 6 | 4 | 2 | 0 - learning python and django 1 - Ran the selenium tests. Required modification to run successfully, need to fix some tests 4 - debuged and testing 5 - attended meeting before class and a call-in meeting 6 - interation planning | 2 | 1 |  |  | 1 | 2 |  | Continue to learn all the tools, I spent time debugging and fixing some of the tests. Took it easy since its spring break | 4
7 (03/02-03/09) Spring Break | 2 | 4 | 2 | 0 - learning python and django 1 - Ran the selenium tests. Required modification to run successfully, need to fix some tests 4 - debuged and testing 5 - attended meeting before class and a call-in meeting 6 - interation planning | 2 |  |  |  |  | 2 |  | Continue to learn all the tools, I spent time researching a code coverage plugin to add to the project. add stories to the current interation and filled in tasks. Took it easy since it spring break | 4
8 (03/09-03/16) Spring Break | 4 | 8 | 2 | 0 - learning python and django 1 - Ran the selenium tests. Required modification to run successfully, need to fix some tests 4 - debuged and testing 5 - attended meeting before class and a call-in meeting 6 - interation planning | 2 |  |  |  |  | 2 |  | Continue to learn all the tools, I spent time analizing the story that is assigned to me. I have some of the feature working just need to finalize a few issues. | 8
9 (03/16-03/23) | 22 | 20 | 2 | 0 - learning python and django 1 - Ran the selenium tests. Required modification to run successfully, need to fix some tests 4 - debuged and testing 5 - attended meeting before class and a call-in meeting 6 - interation planning | 8 |  | 10 |  |  | 2 |  | Continue to learn all the tools, I spent most of the time implement and debugging the new attachment feature. Worked on Upload feature. | 8
10 (03/23-03/30) | 10 | 8 | 2 | 0 - learning python and django 1 - Ran the selenium tests. Required modification to run successfully, need to fix some tests 4 - Implementing features/fixing bugs, debuged and testing 5 - Iteration planning / attended meeting before class and a call-in meeting 6 - interation planning | 4 |  | 4 |  |  | 2 |  | Continue to learn all the tools, I spent most of the time implement and debugging the new attachment feature. Worked on Delete and Download | 8
11 (03/30-04/6) | 6 | 5 | 1 | 0 - learning python and django 1 - Ran the selenium tests. Required modification to run successfully, need to fix some tests 4 - Implementing features/fixing bugs, debuged and testing 5 - attended meeting before class and a call-in meeting 6 - interation planning | 2 | [5 empty] | 3 | Continue to learn all the tools, I spent time researching for a code corage plugin for PyDev. Spent time planning for the final iteration | 8
12 (04/06-04/13) | 7 | 6 | 1 | 0 - learning python and django 1 - Ran the selenium tests. Required modification to run successfully, need to fix some tests 4 - Implementing features/fixing bugs, debuged and testing 5 - attended meeting before class and a call-in meeting 6 - interation planning | 2 | 4 | [5 empty] | Continue to learn all the tools, I spent time setting up and running the code coverage report django. Implementing new unit tests to improve coverage for stroy_comment. | 8
13 (04/13-04/20) | 9 | 8 | 1 | 0 - learning python and django 1 - Ran the code coverage report for a baseline. 3 - Implementing unit tests, debuged and testing 5 - attended meeting before class and a call-in meeting 7 - Preparing for final preasentation | 2 | 1 |  | 2 |  | 1 | 2 | Continue to learn all the tools, I spent time setting up and running the code coverage report django. Implementing new unit tests to improve coverage for story_attachment. Spent time researching how secure is django's security for final presentation. | 8
14 (04/20-04/27) | 7 | 6 | 1 | 0 - learning python and django 5 - attended call-in meeting 7 - Preparing for final preasentation | 3 |  |  |  |  | 1 | 3 | Continue to learn all the tools, I spent time setting up and running the code coverage report django. Implementing new unit tests to improve coverage for story_attachment. Spent time researching how secure is django's security for final presentation. | 8

## Yue Lei
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (01/27-02/03) | 14 | 12 | 2 | 0 - learning python, git (Learning basic grammar of python. Creat a git account and learn basic git operations. Join our team repo.) 1 - gather requirements (Install the previous project management tool and play with it to find bugs or improvements. Compare with other famous management tools) 5 - attend group meeting (Work as the minutes taker and time keeper) | 6 | 6 |  |  |  | 2 |  | Continue to learn all the tool, work on SPPP document, attend meetings | 14
3 (02/03-02/09) | 10 | 8 | 2 | 0 - Keep learning python , django framework related to project code 1 - Finish part 3 for the SPPP document. Creating drafts of stories in Pivotal Tracker 5 - Team meeting on the stories and focus on first iteration | 6 | 2 |  |  |  | 2 |  | Continue to learn the famework and decide requirement finalised in planning phase. | 10
4 (02/10-02/16) | 8 | 6 | 2 | 0 - learning python and django, setup vm environment 4 - learn python unit test 5 - atended meeting after class and a call-in meeting | 4 | 2 |  |  |  | 2 |  | Continue to learn all the tools, Looked at getting the current PyUnit and selemium test working. Having difficutly with GIT trying to checkou a branch. | 8
5 (02/17-02/23) | 12 | 9 | 3 | 0 - learning django, Python unit tests, and Selenium Tests 4 - Fixed existing Selenium tests bugs 5 - Attended group meetings, helped teammates with git configuration and Selenium test. | 4 |  |  |  | 5 | 3 |  | Focus on developing and executing Python unit testing for assigned iteration story | 12
6 (02/24-03/01) | 8 | 6 | 2 | 0 - learned git branches and merge. Python unit and selenium testing 1 - Modify and add stories on Pivotaltracker 4 - Add a new test function in unit test case 5 - Attended group meetings/ conference call , prepare for presentation of iteration 1 | 3 | 1 |  |  | 2 | 2 |  | Focus of fixing bugs we choosed and adding new function | 5
7 (03/02-03/08) Spring Break | 3 | 3 | 0 | 0 - learning python and django 1 - Ran the selenium tests. Required modification to run successfully, need to fix some tests 3 - Discuss on implementation | 1 | 1 |  | 2 |  |  |  | Away from boston for visit, finish homework | 10
8 (03/09-03/15) Spring Break | 10 | 10 | 0 | 0 - learning python and django 3 - Get the assigned part of implementation and prepare for it 6 - Work on homework 3 | 1 |  |  | 2 |  |  | 8 | Continue to learn all the tools and focus on the part I need to implementation | 12
9 (03/16-03/22) | 9 | 7 | 2 | 0 - learning python and HTML 3 - Implementing that each story on the "Project Detail" page should have a work status displayed (unstarted, started, completed, accepted) Changes models of iteration to fix iteration end date bug and make unit test properly to test it 5 - Attended group meetings | 1 |  |  | 6 |  | 2 |  | Accept stories and merge branches | 8
10 (03/23-03/29) | 6 | 4 | 2 | 4 - Code review and help QA leader to finish coverage test report 5 - Attended group meetings/ conference call and work as the minutes taker/time keeper) |  |  |  | 4 |  | 2 |  | Prepare for presentation and finish coverage test report | 6
11 (03/30 - 04/05) | 14 | 12 | 2 | 5 - Attended group meetings/ conference call 6 - Read the code of models and working on homework 4 | [5 empty] | 2 | 12 | prepare for implemention | 10
12 (04/06 - 04/12) | 8 | 6 | 2 | 3 - Modify story model and Implement story types on project 5 - Attended group meetings/ conference call and work as the minutes taker/time keeper) |  |  |  |  | 6 | 2 |  | Prepare for writing unit test | 10
13 (04/12 - 04/19) | 8 | 7 | 1 | 0 - Learn pyunit test from codes 4 - Write unite 6 test cases for model "task" 5 - Attended group meetings/ conference call | 4 |  |  |  | 3 | 1 |  | Prepare for presentation | 6
13 (04/20 - 04/27) | 5 | 4 | 1 | 1 - Finish requirement part of SPPP and part presentation 5 - Attended group meetings/ conference call |  | 4 |  |  |  | 1 |  | Prepare for presentation

## Shucheng Ge
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (01/27-02/03) | 14 | 12 | 2 | 0 - learning python, git (Learning grammar of python. ) 1 - gather requirements (Install the previous project management tool and play with it to find bugs or improvements. Compare with other famous management tools) 5 - attend group meeting (Work as the minutes taker and time keeper) | 6 | 6 |  |  |  | 2 |  | finish the VM installation and continue to learn git hub, like how to build a repository and manipulate it. | 14
3 (02/03-02/09) | 10 | 8 | 2 | 0 - Keep learning python 1 - Finish part 3 for the SPPP document. Creating drafts of stories in Pivotal Tracker 5 - Team meeting on the stories and focus on first iteration | 6 | 2 |  |  |  | 2 |  | Continue to learn the famework and decide requirement finalised in planning phase. | 10
4 (02/10-02/16) | 8 | 6 | 2 | 0 - learning python and django, setup vm environment 4 - learn python unit test 5 - atended meeting after class and a call-in meeting | 4 | 2 |  |  |  | 2 |  | Focus of fixing bugs we choosed and adding new function, Learn the knowledge of the Python and github, (Unitest for python) | 8
5 (02/17-02/23) | 12 | 9 | 3 | 0 - learning django, Python unit tests, and Selenium Tests 4 - Fixed existing Selenium tests bugs 5 - Attended group meetings, helped teammates with git configuration and Selenium test. | 4 |  |  |  | 5 | 3 |  | learn the test code on original project, the UI and the unittest, and fixed the bugs in selenium test | 12
6 (02/24-03/02) | 8 | 6 | 2 | 0 - learned git branches and merge. Python unit and selenium testing 1 - Modify and add stories on Pivotaltracker 4 - Add a new test function in unit test case 5 - Attended group meetings and conference call , prepare for presentation of iteration 1 | 3 | 1 |  |  | 2 | 2 |  | fixed the bugs in selenium test and do the code review | 10
03/02 - 03/09 |  |  |  | 0 - spring break | [7 empty] | the spring break
03/10 - 03/16 |  |  |  | 0 - learned Python unit and selenium testing 1 - Modify and add stories on Pivotaltracker 4 - Add a new test function in unit test case 5 - Attended group meetings and conference call , prepare for presentation of iteration 1
3/23-3/29 | 8 | 7 | 1 | 2- prepare the new features in backlog | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0
3/30-4/5 | 6 | 5 | 1 | 3- prepare the new features in backlog 4- write user manul for the python coverage pack | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0
4/6-4/12 | 4 | 2 | 2 | 3- attend the meeting of new backlog features 4- prepare to test project.py | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0
4/13-4/19 | 7 | 6 | 1 | 3-write the model part | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
4/20-4/26 | 4 | 3 | 1 | 3- write the ppt 3- write the testing report | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0

## Vikrant Sanghvi
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (01/27-02/03) | 12 | 10 | 2 | 0 - learning python, git, django, previous project code and getting familiar with previous project code 1 - Suggest the requirement for project in terms of bugs which can be fixed and new features can be added after analysing the available project management tool. 3 - Install the vm disk image and try the local run of project code. 5 - attended group meetings and suggest the ideas for forther work. | 7 | 1 |  | 2 |  | 2 |  | Continue to learn tools and previous project code, work on SPPP document, attend meetings | 12
3(02/03- 02/10) | 12 | 10 | 2 | 0- continue learning python , django framework related to project code 1- finalise or narrow n the requirement important to the system or tool 4- go through the testing scripts of previous project 5- team meeting on sppp and planning phase finalise 6- record the part of sppp document | 5 | 1 |  |  | 3 | 2 | 1 | Continue to learn the famework and work towards the requirement finalised in planning phase. | 8
4(02/10-02/17) | 12 | 10 | 2 | 0- continue learning github for branch and merge and django framework. 1- add story to pivoltal tracker. 4- learn about selenium and QTP framework for unit testing . 5- attend the team meeting to discuss about split of subteams and take bug to run test for iteration 1. | 5 | 1 |  |  | 4 | 2 |  | Continue to work for iteartion 1 by implementing testing on available code. | 8
5(02/17-02/24) | 12 | 10 | 2 | 0- continue learning github for branch and merge and django framework. 1- add story to pivoltal tracker. 4- learn about selenium and QTP framework for unit testing . 5- attend the team meeting to discuss about split of subteams and take bug to run test for iteration 1. | 5 | 1 |  |  | 4 | 2 |  | Continue to work for iteartion 1 by implementing testing on available code. | 8
6 (02/24-03/01) | 11 | 11 | 2 | 0 - learned Python unit and selenium testing, merged code and git maintenance 2 - designed unit tests 3 - Implemented unit tests and fixed Selenium tests 4 - Performed testing of devteam branches 5 - Attended group discussion based on iteration 2 | 2 |  | 1 | 4 | 2 | 2 |  | Focus of fixing identified bugs and adding new functionality
7 (03/02-03/08 | 4 | 4 | 2 | 0 - learned Python and Django 2 - designed improvements to Project Detail 5 - Attended group meetings | 1 |  | 1 |  |  | 2 |  | Focus on developing improvements to Project Detail
8(03/08-03/15) | 8 | 8 | 2 | 0 - learned Python and Django 2 - designed improvements to Project Detail 5 - Attended group meetings | 2 |  | 4 |  |  | 2 |  | Focus on unit test for java as well as python and new feature development.
9 (03/16-03/22) | 13 | 13 | 2 | 0 - learned Python and Django 3 - designed improvements to Project Detail 5 - Attended group meetings | 2 |  |  | 8 | 1 | 2 |  | Focus on developing improvements to Project Detail for Iteration 2
10 (03/22-03/29) | 13 | 13 | 2 | 0 - learned Python and Django 3 - designed improvements to Project Detail, Python unit test scripts 5 - Attended group meetings | 2 |  |  | 8 | 1 | 2 |  | Focus on developing improvements to Project Detail for Iteration 2
11 (03/29-04/06) | 13 | 13 | 2 | 0 - learned Python and Django 3 - designed improvements to Project Detail, Python unit test scripts 5 - Attended group meetings | 2 |  |  | 8 | 1 | 2 |  | Focus on developing improvements to Project Detail for Iteration 2
12 (4/5-4/12) | 13 | 13 | 1 | 0 - learned Python and Django 3 - designed improvements to Project Detail 4 - testing implemented features 5 - Attended group meetings | 0 |  |  | 10 | 2 | 1 |  | Focus on implemeting requirements for Iteration 3
13 (4/12-4/19) | 3 | 3 | 1 | 0 - learned Python and Django 3 - designed improvements to Project Detail 4 - testing implemented features 5 - Attended group meetings | 0 |  |  | 1 | 1 | 1 |  | Focus on testing for Iteration 3
13 (04/20 - 04/27) | 5 | 4 | 1 | 1 - Finish requirement part of SPPP and part presentation 5 - Attended group meetings/ conference call |  | 4 |  |  |  | 1 |  | Prepare for presentation