## Samer Abu-Nasser
Project 13 - Issue Tracker
ending date | week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Total estimated time | comments
2015-02-04 | 3 | Samer Abu-Nasser | 21.5 | +8 - learning docker +5 - refreshing html/css +5 - learning git +5 - setup enviroment and begin setups +0.5 meeting minutes | 2 | 0 - learning tools 2 - infrastructure design 4 - infrastructure test 5 - attend group meeting | 14 | 0 | 0 | 0 | 5 | 0.5 | 0 | 21.5 | -learn docker -deploy test docker enviroment -setup operating system and containers with mysql, python enviroment and git -complete meeting minutes -by next week distribute an image of docker and a short tutorial on how to use (commit) copy and work on
2015-02-11 | 4 | Samer Abu-Nasser | 17.5 | +13 learning django +2 interface design mockups +0.5 meeting minutes | 2 | 0 - learning, setup enviroment 5 - communitation/planning/management 2 - design | 15 | 0 | 0 | 0 | 0 | 0.5 | 0 | 17.5
2015-02-18 | 5 | Samer Abu-Nasser | 16 | +15 learning django | 1 | 0 - learning, setup enviroment | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 16
2015-02-25 | 6 | Samer Abu-Nasser | 17 | +15 learning django +2 class model | 0 | 0 - learning, setup enviroment 2 - design | 15 | 0 | 2 | 0 | 0 | 0 | 0 | 17
2015-03-11 | 7 | Samer Abu-Nasser | 16 | +15 learning django | 1 | 0 - learning, setup enviroment | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 16
2015-03-18 | 8 | Samer Abu-Nasser | 20.5 | +15 learning django +4 setup server + 0.5 meeting minutes | 1 | 0 - learning, setup enviroment 5 - communitation/planning/management 2 - design 3 - implementation | 15 | 0 | 0 | 4 | 0 | 0.5 | 0 | 20.5
2015-03-25 | 9 | Samer Abu-Nasser | 26 | +5 local dev enviroment test and understanding +5 enviroment and integration research +14 learning django | 1 | 5 - communitation/planning/management 2 - design 3 - implementation | 14 | 5 | 0 | 5 | 0 | 1 | 0 | 26
2015-04-01 | 10 | Samer Abu-Nasser | 34 | +7 local dev enviroment test and understanding +5 enviroment and integration research +20 learning django | 1 | 0 - learning, setup enviroment 3- implementation 5 - communitation/planning/management | 20 | 7 | 0 | 5 | 0 | 1 | 0 | 34
2015-04-08 | 11 | Samer Abu-Nasser | 31 | +7 local dev enviroment test and understanding +5 enviroment and integration research +15 learning django | 2 | 5 - communitation/planning/management 2 - design 3 - implementation | 15 | 7 | 0 | 5 | 0 | 2 | 0 | 31
2015-04-15 | 12 | Samer Abu-Nasser | 29 | '+10 enviroment and integration research +15 learning django | 2 | 5 - communitation/planning/management 2 - design 3 - implementation | 15 | 10 | 0 | 0 | 0 | 2 | 0 | 29
2015-04-22 | 13 | Samer Abu-Nasser | 29 | +10 merge code bases part I '+5 understand codebase '+10 finalize bugs and deploy pre server | 2 | 0 - learning codebase 5 - communitation/planning/management 15 - implementation | 5 | 0 | 0 | 20 | 0 | 2 | 0 | 29
2015-04-29 | 14 | Samer Abu-Nasser | 30 | +5 meet with group and work on project '+15 finalize bugs nad deploy pro server '+4 create diagrams for presentation '+4 create presentation | 5 | 5 - communitation/planning/management 2 - design 3 - implementation | 0 | 0 | 4 | 15 | 2 | 4 | 0 | 30

## Jerrold Ansman
Project 13 - Your Project Name
week # | Week Ending | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
3 | 2015-02-04 | Jerrold Ansman | 12 | 9.5 | 2.5 | 0 - learning tools:Github,Git, Python, Django, Setting up Pivotal Tracker for Group 5 - attend group meeting, discuss, emails with Team Leads | 7 |  |  |  |  | 5 |  | 10 | 10
4 | 2015-02-11 | Jerrold Ansman | 13 | 8 | 5 | 0 - Django Tutorial, 2 - HTML design work, 5 - Team Meetings, response to Slack questions. | 3 |  | 3 |  |  | 7 |  |  | 10
5 | 2015-02-18 | Jerrold Ansman | 29 | 26.75 | 2.25 | 0 - Django Tutorial and Learning, Learning Bootstrap, Additional elements of GitHub, Downloaded and learned Pep8 and Pyflakes for testing purposes; 3 - Django and HTML code for Issue Index page, updates Python code in order to make page working with other pages, updated pages to all implement the same base.html page and css; 5 - Communicated with Team members and other Teams regarding requirements of the projects and answer questions via Slack. | 15 |  |  | 8 |  | 6 |  | 15 | 10
6 | 2015-02-25 | Jerrold Ansman | 7 | 5.5 | 1.5 | 2 - Created a multiple issue table. 3 - Wrote code for a dynamic index of issues. |  |  | 1.5 | 3 |  | 1 |  |  | 10
7 | 2015-03-04 | Jerrold Ansman | 13 | 12 | 1 | 2 - Design work done for edit issue page. 3 - Django and HTML coding and implementation for several pages. Worked with updating CSS throughout pages. 5 - Communicated with team members and other team as part of group leader role. |  |  | 2 | 8 |  | 2 |  | 15 | 10
8 | 2015-03-11 | Jerrold Ansman | 0 | 0 | 1 | Spring Break | [7 empty] | 0 | 0
9 | 2015-03-18 | Jerrold Ansman | 3.5 | 2 | 1.5 | 2 - Began working on sorting function of multiple issue table. |  |  | 2 |  |  |  |  | 10 | 10
10 | 2015-03-25 | Jerrold Ansman | 9 | 7.5 | 1.5 | 3 - CSS work on sidebar, highlight hover over option. Updated history section and worked on Edit Issue Page. |  |  |  | 7.5 |  |  |  | 10 | 10
11 | 2015-04-01 | Jerrold Ansman | 9.5 | 8 | 1.5 | 3 - Continued working on Edit Issue page. |  |  |  | 8 |  |  |  | 10 | 10
12 | 2015-04-08 | Jerrold Ansman | 7.5 | 6 | 1.5 | 3 - HTML/CSS work to update Edit and View Detail pages to have same format. |  |  |  | 6 |  |  |  | 10 | 10
13 | 2015-04-15 | Jerrold Ansman | 5.5 | 4 | 1.5 | 2- Updated issue model with classifications in line with Professor's idea. |  |  | 2 | 2 |  |  |  | 10 | 10
14 | 2015-04-22 | Jerrold Ansman | 8.5 | 7 | 1.5 | 3 - HTML/CSS code clean-up on all pages. Correct "Edit Issue" button to work on different browsers. |  |  |  | 7 |  |  |  | 10 | 10
15 | 2015-04-29 | Jerrold Ansman | 11 | 8 | 3 | 3 - HTML coding for navigation sidebar to transverse to other tools. 5 - Communications with all teams during integration. |  |  |  | 3 |  | 5 |  | 10 | 10

## Joshua Darrieulat
Project 13 - Issue Tracker
Ending date | week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 7 tasks | Estimated tasks for next week | Total estimated time
2015-02-04 | 3 | Joshua Darrieulat | 10 | 3 hr - group meeting 1 hr - Redmine 1 hr - Github feature analysis 2 hr - Github setup/support 1 hr - Python support 1 hr - Django tutorial 1 hr - Learning GIT client | 2 | 0 - learning Git, reading up on Django, Setting up github for everyone, python support, 1 - Reviewed Redmine and Github issue tracker for feature set and passed it along to the group 5 - Met with group, including travel time to get to group. | 5 | 2 |  |  |  | 3 |  |  | 10
2015-02-11 | 4 | Joshua Darrieulat | 20 | 15 hr - Create initial Django app 3 hr - two meetings with team 2 hr - create mockups and stories | 3 | 0 - continued reading on django app 2 - designed an initial django app for the team to build on. 3 - implemented the inital app 4 - Created example tests for the app 5 - Met with group, created 3 stories, created 3 mock-ups | 2 |  | 2 | 11 | 1 | 4 |  |  | 20
2015-02-18 | 5 | Joshua Darrieulat | 20.5 | 3 hr - met with team 15.5 hr - Create issue tracker first setup. | 2 | 0 - Continued reading on models in django 2 - designed a model for the issue tracker app 3 - implemented an initial issue tracker app on top of model. This included createIssue, viewIssue, and began work on search. 4 - Created a population script for users to allow team to setup users automatically. 5 - Met with group, Worked through breakdown of work with them, Heavy communication 7 - made and presented on Django Architecture | 2 |  | 5 | 7 | 1.5 | 3 | 2 |  | 20.5
2015-02-25 | 6 | Joshua Darrieulat | 15 | 1.5 hr - met with team 13hr - create REST support for project and fix bugs. | 1 | 0 - Read up on djangorestframework and setup 2 - Put together a design for putting in an initial REST interface to Issue model. 3 - Added rest browsing and support to the application. Numerous bugfixes added. Also added an issue population script. 5 - Communicated with the team those changes. Also dealt with coordination and changes which were all merged in. | 3 |  | 1 | 8 | 1 | 2 |  |  | 15
2015-03-04 | 7 | Joshua Darrieulat | 11 | 2 hr - met with team 9 hr - create search and bug fixes | 2 | 0 - Read up on querysets in django 2 - Put together a design for searching issues 3 - Added support for issue search to application. and did more bug fixes. 5 - Met with and communicated with team | 2 |  | 1 | 6 |  | 2 |  |  | 11
2015-03-11 | 8 | Joshua Darrieulat | 0 | Spring break | 0 |  | 0 | [7 empty] | 0
2015-03-18 | 9 | Joshua Darrieulat | 5 | 2 hr - met with team 1 hr - researched dates for search problem 2 hr - team support | 2 | 0 - reading further on querysets 5 - Team support and meetings | 1 |  |  |  |  | 4 |  |  | 5
2015-03-25 | 10 | Joshua Darrieulat | 16 | 3 hr - met with team 1 hr - research how to solve search problem 2 hr - team support 8 hr - refactoring, bug fixes and completing search | 2 | 0 - Reading further on querysets 3 - Completed search functionality, Bug fixes, 4 - Refactored testing code to use a common base class. 5 - Met with and supported team | 1 |  |  | 8 | 2 | 5
2015-04-01 | 11 | Joshua Darrieulat | 6 | 4 hr - Met and supported team 2 hr - bug fixes | 2 | 3 - Bug fixes 5 - Team meeting and support |  |  |  | 2 |  | 4
2015-04-08 | 12 | Joshua Darrieulat | 6 | 4 hr - Met and supported team 2 hr - bug fixes | 2 | 3 - Added support for demo data with comments, bug fixes 5 - Team meeting and support |  |  |  | 2 |  | 4
2015-04-15 | 13 | Joshua Darrieulat | 7 | 4 hr - Met and supported team 2 hr - bug fixes | 2 | 3 - Bug fixes 5 - Team meeting and support |  |  |  | 2 |  | 5
2015-04-22 | 14 | Joshua Darrieulat |  | Frozen: Integration occurring
2015-04-29 | 15 | Joshua Darrieulat | 8 | 4 hr - Met and supported team 4 hr - bug fixes | 2 | 3 - Last minute cleanup, integration of the Project model and population 5 - Meetings and team support |  |  |  | 4 |  | 4
Project 13 - Your Project Name
| week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
| 3 | Lin-Kei Tseng (Ted) | 23 | 5hr - search data +1 - small group meeting +3 - LOGO +5 - set up Python and learn Git +4 - JIRA +3 - Git | 2 | 0 - learning tools:Github,BugZilla,JIRA,Python,Git 5 - attend group meeting, discuss. ... 2 - design LOGO | 3+5+3 | 5+4 | 3 |  |  | 2 |  | 10 | 10
| 3 | Joshua Darrieulat | 10 | 3 hr - group meeting 1 hr - Redmine 1 hr - Github feature analysis 2 hr - Github setup/support 1 hr - Python support 1 hr - Django tutorial 1 hr - Learning GIT client | 2 | 0 - learning Git, reading up on Django, Setting up github for everyone, python support, 1 - Reviewed Redmine and Github issue tracker for feature set and passed it along to the group 5 - Met with group, including travel time to get to group. | 5 | 2 |  |  |  | 3 |  |  | 10
10
10
10
10
Project 13 - Your Project Name
| week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
| 3 | Lin-Kei Tseng (Ted) | 23 | 5hr - search data +1 - small group meeting +3 - LOGO +5 - set up Python and learn Git +4 - JIRA +3 - Git | 2 | 0 - learning tools:Github,BugZilla,JIRA,Python,Git 5 - attend group meeting, discuss. ... 2 - design LOGO | 3+5+3 | 5+4 | 3 |  |  | 2 |  | 10 | 10
| 3 | Joshua Darrieulat | 10 | 3 hr - group meeting 1 hr - Redmine 1 hr - Github feature analysis 2 hr - Github setup/support 1 hr - Python support 1 hr - Django tutorial 1 hr - Learning GIT client | 2 | 0 - learning Git, reading up on Django, Setting up github for everyone, python support, 1 - Reviewed Redmine and Github issue tracker for feature set and passed it along to the group 5 - Met with group, including travel time to get to group. | 5 | 2 |  |  |  | 3 |  |  | 10
10
10
10
10
Project 13 - Your Project Name
| week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
| 3 | Lin-Kei Tseng (Ted) | 23 | 5hr - search data +1 - small group meeting +3 - LOGO +5 - set up Python and learn Git +4 - JIRA +3 - Git | 2 | 0 - learning tools:Github,BugZilla,JIRA,Python,Git 5 - attend group meeting, discuss. ... 2 - design LOGO | 3+5+3 | 5+4 | 3 |  |  | 2 |  | 10 | 10
| 3 | Joshua Darrieulat | 10 | 3 hr - group meeting 1 hr - Redmine 1 hr - Github feature analysis 2 hr - Github setup/support 1 hr - Python support 1 hr - Django tutorial 1 hr - Learning GIT client | 2 | 0 - learning Git, reading up on Django, Setting up github for everyone, python support, 1 - Reviewed Redmine and Github issue tracker for feature set and passed it along to the group 5 - Met with group, including travel time to get to group. | 5 | 2 |  |  |  | 3 |  |  | 10
10
10
10
10
Project 13 - Your Project Name
| week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
| 3 | Lin-Kei Tseng (Ted) | 23 | 5hr - search data +1 - small group meeting +3 - LOGO +5 - set up Python and learn Git +4 - JIRA +3 - Git | 2 | 0 - learning tools:Github,BugZilla,JIRA,Python,Git 5 - attend group meeting, discuss. ... 2 - design LOGO | 3+5+3 | 5+4 | 3 |  |  | 2 |  | 10 | 10
| 3 | Joshua Darrieulat | 10 | 3 hr - group meeting 1 hr - Redmine 1 hr - Github feature analysis 2 hr - Github setup/support 1 hr - Python support 1 hr - Django tutorial 1 hr - Learning GIT client | 2 | 0 - learning Git, reading up on Django, Setting up github for everyone, python support, 1 - Reviewed Redmine and Github issue tracker for feature set and passed it along to the group 5 - Met with group, including travel time to get to group. | 5 | 2 |  |  |  | 3 |  |  | 10
10
10
10
10
Project 13 - Your Project Name
| week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
| 3 | Lin-Kei Tseng (Ted) | 23 | 5hr - search data +1 - small group meeting +3 - LOGO +5 - set up Python and learn Git +4 - JIRA +3 - Git | 2 | 0 - learning tools:Github,BugZilla,JIRA,Python,Git 5 - attend group meeting, discuss. ... 2 - design LOGO | 3+5+3 | 5+4 | 3 |  |  | 2 |  | 10 | 10
| 3 | Joshua Darrieulat | 10 | 3 hr - group meeting 1 hr - Redmine 1 hr - Github feature analysis 2 hr - Github setup/support 1 hr - Python support 1 hr - Django tutorial 1 hr - Learning GIT client | 2 | 0 - learning Git, reading up on Django, Setting up github for everyone, python support, 1 - Reviewed Redmine and Github issue tracker for feature set and passed it along to the group 5 - Met with group, including travel time to get to group. | 5 | 2 |  |  |  | 3 |  |  | 10
10
10
10
10
Project 13 - Your Project Name
| week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
| 3 | Lin-Kei Tseng (Ted) | 23 | 5hr - search data +1 - small group meeting +3 - LOGO +5 - set up Python and learn Git +4 - JIRA +3 - Git | 2 | 0 - learning tools:Github,BugZilla,JIRA,Python,Git 5 - attend group meeting, discuss. ... 2 - design LOGO | 3+5+3 | 5+4 | 3 |  |  | 2 |  | 10 | 10
| 3 | Joshua Darrieulat | 10 | 3 hr - group meeting 1 hr - Redmine 1 hr - Github feature analysis 2 hr - Github setup/support 1 hr - Python support 1 hr - Django tutorial 1 hr - Learning GIT client | 2 | 0 - learning Git, reading up on Django, Setting up github for everyone, python support, 1 - Reviewed Redmine and Github issue tracker for feature set and passed it along to the group 5 - Met with group, including travel time to get to group. | 5 | 2 |  |  |  | 3 |  |  | 10
10
10
10
10
Project 13 - Your Project Name
| week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
| 3 | Lin-Kei Tseng (Ted) | 23 | 5hr - search data +1 - small group meeting +3 - LOGO +5 - set up Python and learn Git +4 - JIRA +3 - Git | 2 | 0 - learning tools:Github,BugZilla,JIRA,Python,Git 5 - attend group meeting, discuss. ... 2 - design LOGO | 3+5+3 | 5+4 | 3 |  |  | 2 |  | 10 | 10
| 3 | Joshua Darrieulat | 10 | 3 hr - group meeting 1 hr - Redmine 1 hr - Github feature analysis 2 hr - Github setup/support 1 hr - Python support 1 hr - Django tutorial 1 hr - Learning GIT client | 2 | 0 - learning Git, reading up on Django, Setting up github for everyone, python support, 1 - Reviewed Redmine and Github issue tracker for feature set and passed it along to the group 5 - Met with group, including travel time to get to group. | 5 | 2 |  |  |  | 3 |  |  | 10
10
10
10
10
Project 13 - Your Project Name
| week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
| 3 | Lin-Kei Tseng (Ted) | 23 | 5hr - search data +1 - small group meeting +3 - LOGO +5 - set up Python and learn Git +4 - JIRA +3 - Git | 2 | 0 - learning tools:Github,BugZilla,JIRA,Python,Git 5 - attend group meeting, discuss. ... 2 - design LOGO | 3+5+3 | 5+4 | 3 |  |  | 2 |  | 10 | 10
| 3 | Joshua Darrieulat | 10 | 3 hr - group meeting 1 hr - Redmine 1 hr - Github feature analysis 2 hr - Github setup/support 1 hr - Python support 1 hr - Django tutorial 1 hr - Learning GIT client | 2 | 0 - learning Git, reading up on Django, Setting up github for everyone, python support, 1 - Reviewed Redmine and Github issue tracker for feature set and passed it along to the group 5 - Met with group, including travel time to get to group. | 5 | 2 |  |  |  | 3 |  |  | 10
10
10
10
10

## Joe Driver
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
3 | Joe Driver | 12 | 10.5 | 1.5 | Spent a good amount of time training people to use git. Included setting up a practice repo for people to work with. Some time was also allotted for communication and planning with other QA leads, group leads etc. Additional time in requirement analysis of 2 Issue trackers, and maintenance of the tracking sheet. | 6 | 2 |  |  | 1 | 1 | 2 | will be filled out after team meeting wednesday
4 | Joe Driver | 16 |  | 3 | 0- Learning HTML Learning CSS Learning Visual Paradigm Django Tutorial 1- Planning for mockups and use case models User Stories, SPPP doc 2- Issue page mockup. Issue Page html doc Use Case Diagram 5- Prep for two meetings, follow up on assignments and deadline management Review of submitted work Meeting Minutes, git config | 2 | 2 | 4 | 0 | 0 | 5 |  | Implementation and further development of front end
5 | Joe Driver | 12 | 11 | 1 | 0- Understanding REST Additional Bootstrap education QA for other teammates 3- Additional stitching of existing pages together, CSS and html cleanup, general code cleanup and standardization 4- Git management and code review 5- Presentation Outline and Base Meeting prep & Meeting | 3 |  |  | 4 | 1.5 | 2.5
6-7 (spring break) | Joe Driver |  |  | 1 | 0- Setting up Selenium on Windows, resolving issues with virtual environments and PATH variable | 4 |  |  |  | 6 | 2

## Chun-Kai Huang
Project 13 - Your Project Name
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2015-02-04 | Chun-Kai Huang (Kenny) | 11 | 11 | 2 | 0 - Python,Django,Git,Github,BugZilla,Lighthouse 3 - Basic python application 5 - Group meeting | 6 |  |  | 2 |  | 2 |  | 10 | 10
2015-02-11 | Chun-Kai Huang (Kenny) | 18 | 14.5 | 3.5 | 1 - User story 2 - Issue report mockup, SPPP, html design 5 - Group meeting |  | 3 | 8 |  |  | 3.5 |  | 10 | 10
2015-02-18 | Chun-Kai Huang (Kenny) | 19 | 16 | 3 | 1 - Python,Django 2 - Edit Issue 5 - Group meeting |  | 3 | 10 |  |  | 3 |  | 10 | 10
2015-02-25 | Chun-Kai Huang (Kenny) | 15 | 13.5 | 1.5 | 1 - Python,Django 2 - Edit Issue, Iteration1 presentation prepare 5 - Group meeting |  | 4 | 8 |  |  | 1.5 |  | 10 | 10
2015-03-04 | Chun-Kai Huang (Kenny) | 12.5 | 11 | 1.5 | 1 - Python,Django 2 - Edit Issue function 5 - Group meeting |  | 3 | 8 |  |  | 1.5 |  | 10 | 10
2015-03-11 | Chun-Kai Huang (Kenny) | 12 | 10 | 2 | 1 - Python,Django 2 - Edit/View Issue 5 - Group meeting |  | 3 | 7 |  |  | 2 |  | 10 | 10
2015-03-18 | Chun-Kai Huang (Kenny) | 14.5 | 13 | 1.5 | 1 - Python,Django, Html, CSS 4 - Testing 5 - Group meeting |  | 5 |  |  | 8 | 1.5 |  | 10 | 10
2015-03-25 | Chun-Kai Huang (Kenny) | 10 | 9 | 1 | 1 - Python,Django, Html, CSS 4 - Testing 5 - Group meeting |  | 3 |  |  | 6 | 1 |  | 10 | 10
2015-04-01 | Chun-Kai Huang (Kenny) | 14.5 | 13 | 1.5 | 1 - Python,Django, Bootstrap 2 - Side Navigation & Mobile View 5 - Group meeting |  | 4 | 9 |  |  | 1.5 |  | 10 | 10
2015-04-08 | Chun-Kai Huang (Kenny) | 12 | 10 | 2 | 1 - Python,Django, Bootstrap 2 - Mobile View 5 - Group meeting |  | 2 | 8 |  |  | 2 |  | 10 | 10
2015-04-15 | Chun-Kai Huang (Kenny) | 16 | 14 | 2 | 1 - Python,Django, Bootstrap 2 - Mobile View 5 - Group meeting 6 - Review exercise |  | 2 | 2 |  |  | 2 | 10 | 10 | 10
2015-04-22 | Chun-Kai Huang (Kenny) | 13.5 | 12 | 1.5 | 1 - Python,Django,html, CSS 2 - Additional Mobile View function 5 - Group meeting 6 - Review exercise |  | 1 | 3 |  |  | 1.5 | 8 | 10 | 10
2015-04-29 | Chun-Kai Huang (Kenny) | 12 | 10 | 2 | 1 - Python,Django 2 - Maintain template 5 - Group meeting 6 - Prepare presentation |  | 1 | 2 |  |  | 2 | 7 | 10 | 10

## Ya-Lan (Amy)
Project 13 - Issue Tracker
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
3 (2/4-2-10) | Ya-Lan Tsao (Amy) | 17 | 5+1+5+4 | 2 | 0 - learning tools: Github, BugZilla, Basecamp,Git, Python 5 - Group meeting, discuss. 1 - requirement analysis | 10 | 5 |  |  |  | 2 |  |  | 10
4 (2/11-2/17) | Ya-Lan Tsao (Amy) | 21.5 | 5+5+8 | 3.5 | 0 - Django 1 - User stories,SPPP 2 - Time tracking mockup, HTML-create issue page 5 - Group meeting, discuss. | 5 | 5 | 8 | 0 | 0 | 3.5 | 0
5 (2/18-2/24) | Ya-Lan Tsao (Amy) | 15 | 4+3+5 | 3 | 0 - Bootstrap 2 - Create issue page with bootstrap and connect with our main page 5 - Group meeting | 4 |  | 3+5 |  |  | 3 |  | 3-implementation 0-learning
6 (2/25-3/3) | Ya-Lan Tsao (Amy) | 11.5 | 10 | 1.5 | 0 - Python, Django 3 - working on edit issue page 5 - Group meeting | 5 |  |  | 5 |  | 1.5 |  | 0-learning 3-implementation
7 (3/4-3/10)+ spring break | Ya-Lan Tsao (Amy) | 13 | 11 | 2 | 0 - Python, Django 3 - work on edit issue page (edit function) 5 - Group meeting/ communication in Slack | 3 |  |  | 8 |  | 2
8 (3/18-3/24) | Ya-Lan Tsao (Amy) | 14 | 12 | 2 | 0 - Python, Django 3 - work on edit issue page 5 - Group meeting/ communication in Slack | 2 |  |  | 10 |  | 2
9 (3/25-3/31) | Ya-Lan Tsao (Amy) | 10 | 8 | 2 | 0 - Python, Django 3 - designed and built comment model 5 - Group meeting/ communication in Slack | 3 |  |  | 3 |  | 4
10 (4/1-4/7) | Ya-Lan Tsao (Amy) | 15 | 13 | 2 | 0 - Python, Django 3 - work on add comment function in view issue detail page 5-Group meeting/ communication in Slack | 4 |  |  | 9 |  | 2
11 (4/8-4/14) | Ya-Lan Tsao (Amy) | 10 | 8 | 2 | 0 - Python, Django 3 - show all related comments in current issue detail page/ Update comment model to support showing differrent type of comments in differnt style (normal comment and issue edit report)/ When edit a issue will also add a issue edit report in comment table 5-Group meeting/ communication in Slack | 2 |  |  | 6 |  | 2
12 (4/15-4/21) | Ya-Lan Tsao (Amy) | 7 | 6 | 1 | 0 - Python, Django 3 - Made isssue edit report include old value and updated value/ Funtion Reported page, Closed page and Verified page 5 - Group meeting/ communication in Slack | 2 |  |  | 4 |  | 1
(4/22-4/28) | Ya-Lan Tsao (Amy) | 7.5 | 6 | 1.5 | 3 - reorganize the issue order and fix comment with comment number/ change cursor to hand when mouse hover to the title of sortable colume 5 - Communication in Slack/ weekend in person meeting 6 - Prepare presentation (case diagram/ requirement ) |  |  |  | 2 |  | 1.5 | 4

## Lin-Kei Tseng(Ted)
Project 13 - Issue Tracker
Ending date | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning, setup envionment 1- requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/planning/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2015-02-04 | Lin-Kei Tseng (Ted) | 23 | 5hr - search data +1 - small group meeting +3 - LOGO +5 - set up Python and learn Git +4 - JIRA +3 - Git | 2 | 0 - learning tools:Github,BugZilla,JIRA,Python,Git 5 - attend group meeting, discuss. ... 2 - design LOGO | 3+5+3 | 5+4 | 3 | 0 | 0 | 2 | 0 | 10 | 10
2015-02-11 | Lin-Kei Tseng (Ted) | 16.5 | 13 | 3.5 | 5 - attend group meeting, discuss. ... 1- User stories, manhour , estimate of the story in terms of point 1- SPPP 2 - Dashboard mockup, HTML-Design view issue report | 0 | 5 | 8 | 0 | 0 | 3.5 | 0 | 10 | 10
2015-02-18 | Lin-Kei Tseng (Ted) | 13 | 10 | 3 | 0 - learning tools:Github,Python,Bootstrap 5 - attend group meeting, discuss. ... 2 - Dashboard Design | 5 | 0 | 5 | 0 | 0 | 3 | 0 | 10 | 10
2015-02-25 | Lin-Kei Tseng (Ted) | 12 | 10 | 2 | 0 - learning tools:Python,Django 5 - attend group meeting, discuss. ... 2 - Testing Outline Design | 4 | 0 | 6 | 0 | 0 | 2 | 0 | 10 | 10
2015-03-04 | Lin-Kei Tseng (Ted) | 8.5 | 7 | 1.5 | 0 - learning tools:Python,Django,Selenium 5 - attend group meeting, discuss. ... 4 - Testing Selenium | 2 | 0 | 1 | 0 | 4 | 1.5 | 0 | 5 | 5
2015-03-11 | Lin-Kei Tseng (Ted) | 9 | 7 | 2 | 0 - learning tools:Python,Django,Selenium 5 - attend group meeting, discuss. ... 4 - Testing_Selenium | 2 | 0 | 1 | 0 | 4 | 2 | 0 | 6 | 6
2015-03-18 | Lin-Kei Tseng (Ted) | 9.5 | 8.5 | 1 | 0 - learning tools:Python,Django,Selenium 5 - attend group meeting, discuss. ... 4 - Testing Edit issue | 2 | 0 | 0.5 | 0 | 6 | 1 | 0 | 5 | 5
2015-03-25 | Lin-Kei Tseng (Ted) | 9 | 8 | 1 | 0 - learning tools:Python,Django,Selenium 5 - attend group meeting, discuss. ... 2 - Testing Search issue | 2 | 0 | 0 | 0 | 6 | 1 | 0 | 5 | 5
2015-04-01 | Lin-Kei Tseng (Ted) | 9 | 8 | 1 | 0 - learning tools:Python,Django 5 - Attend group meeting, discuss. ... 3 - Search page_DatePicker (website design) | 4 | 0 | 0 | 4 | 0 | 1 | 0 | 5 | 5
2015-04-08 | Lin-Kei Tseng (Ted) | 6 | 5 | 1 | 0 - learning tools:Python,Django 5 - Attend group meeting, discuss. ... 3 - Search page_CSS (website design) | 2 | 0 | 0 | 3 | 0 | 1 | 0 | 5 | 5
2015-04-15 | Lin-Kei Tseng (Ted) | 11 | 10 | 1 | 0 - learning tools:Python,Django 5 - Attend group meeting, discuss. ... 3 - Search page_CSS (website design) 6 - SE review excercise | 1 | 0 | 0 | 5 | 0 | 1 | 4 | 4 | 4
2015-04-22 | Lin-Kei Tseng (Ted) | 5 | 3 | 2 | 0 - learning tools:Python,Django 5 - Attend group meeting, discuss. ... 3 - Side-Bar_add count function (website design) 6 - SE review excercise | 1 | 0 | 0 | 6 | 0 | 2 | 4 | 6 | 6
2015-04-29 | Lin-Kei Tseng (Ted) | 10 | 8 | 2 | 0 - learning tools:Python,Django 5 - Attend group meeting, discuss. ... 3 - Side-Bar_add icon (website design) 6- prepare powerpoint for presentation | 2 | 0 | 0 | 1 | 0 | 2 | 5 | 0 | 6