## example
CS673T1_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (09/19-09/26) | 5 | 4 | 1 | 0 - learning git, django 1 - discuss project requirement 5 - team meeting | 2 | [6 empty] | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6

## Steve Black
CS673F16T1_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (09/19-09/26) | 3 | 2 | 1 |  |  | 1 | 1 | 0 | 0 | 1 | 0 | 0 - analyze the existing product 3 - fork the repository for existing product 5 - compile and distribute best practices for managing git | 6
3 (9/27-10/3) | 4 | 3 | 1 |  | 1 | 1 | 1 | 0 | 0 |  | 0 | 1 - user stories 2 - feature analysis and planning | 5
4 (10/4-10/10) | 5 | 4 | 1 |  | 1 | 1 | 1 | 0 | 0 |  | 0 |  | 5
5 (10/11-10/17) | 4 | 3 | 1 |  | 0 | 1 | 1 | 1 | 0 |  | 0 | 0 - learning Django and Docker 2 - designing API w/ Django models 3 - implement initial methods | 5
6 (10/18-10/24) | 6 | 6 | 1 |  | 1 | 0 | 2 | 2 | 0 | 1 | 0 | 1 - analyze reqs for iteration 2 2 - design for new reqs 3 - implementation | 5
7(10/25-10/31) | 5 | 4 | 1 |  | 0 | 2 | 2 | 0 | 0 | 1 | 0 | 2 - design of remaining API endpoints 5 - group meeting and admin stuff 1 - keep looking at reqs | 6
8(11/1-11/7) | 5 | 4 | 1 |  | 0 | 1 | 3 | 0 | 0 | 1 | 0 | 3 - implement some of the API endpoints | 6
9(11/8-11/14) | 5 | 4 | 1 |  | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 0 - learn about authentication options for the app | 6
10(11/15-11/21) | 6 | 5 | 1 |  | 1 | 0 | 2 | 1 | 1 | 1 | 0 | 0 - learn about how the existing chat client works 2 - design chat client parsing functionality | 6
11(11/22-11/28) | 5 | 4 | 1 |  | 1 | 0 | 1 | 1 | 1 | 2 | 0 | 5 - merge code from other team members 2 - design chat client parsing functionality 4 - free form testing | 6
12(11/29-12/5) | 6 | 3 | 3 |  | 0 | 1 | 2 | 1 | 1 | 1 | 0 | 3 - implement final user stories 5 - compile project documents 4 - test features | 10
13(12/6-12/12) | 10 | 5 | 5 |  | 0 | 0 | 1 | 4 | 2 | 3 | 0 | N/A! | N/A

## Anthony Valencia
CS673F16T1_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (09/19-09/26) | 5 | 4 | 0.5 |  | 4 |  |  |  |  | 1 |  | review code | 5
3 (9/27-10/3) | 6 | 6 | 0.5 |  | 2 | 1 | 1 | 1 | 1 |  |  | convert dev/deploy environment from virtualenv to Docker | 8
4 (10/4-10/10) | 7 | 5 | 1 |  |  |  | 2 | 2 | 1 | 2 |  | convert dev/deploy environment from virtualenv to Docker | 4
5 (10/11-10/17) | 7 | 6 | 0.5 |  | 2 | 1 | 2 | 1 |  | 1 |  | remotely host static files (including attachments) | 5
6 (10/18-10/24) | 6 | 5 | 0.5 |  |  |  | 2 | 2 | 1 | 1 |  | remotely host static files (including attachments) | 3
7(10/25-10/31) | 8 | 7 | 1 |  | 2 | 1 | 1 | 2 | 1 | 1 |  | debug serialization for issue tracker's REST API calls | 4
8(11/1-11/7) | 8 | 7 | 0.5 |  | 3 |  |  | 3 | 1 | 1 |  | code refactoring, remove unreachable code | 8
9(11/8-11/14) | 8 | 7 | 0.5 |  | 3 |  |  | 3 | 1 | 1 |  | code refactoring, remove unreachable code | 8
10(11/15-11/21) | 8 | 7 | 0.5 |  | 5 |  | 2 |  |  | 1 |  | replace node-based chat application with Django channels-based chat applicatoin | 10
11(11/22-11/28) | 6 | 5 | 1 |  | 1 |  | 2 | 2 |  | 1 |  | replace node-based chat application with Django channels-based chat applicatoin | 10
12(11/29-12/5) | 10 | 9 | 1 |  | 1 |  | 1 | 5 | 2 | 1 |  | replace node-based chat application with Django channels-based chat applicatoin | 6
12(12/6-12/12) | 6 | 5 | 2 |  | 1 |  | 1 | 2 | 1 | 1 |  | add token-based REST authentication | 8

## Demetrius Glover
CS673F16T1_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (09/19-09/26) | 3 | 2 | 1 |  | 1 | 1 |  |  |  | 1 |  | 2 | 2
3 (9/27-10/3) | 3 | 2 | 1 |  | 1 | 1 |  |  |  | 1 |  | 2 | 2
4 (10/4-10/10) | 3.5 | 2.5 | 1 |  | 0.5 | 1 | 1 |  |  | 1 |  | 3 | 2.5
5 (10/11-10/17) | 4 | 4 | 0 |  | 3 | 1 |  |  |  | 1
6 (10/18-10/24) | 4 | 3 | 1 |  | 3 |  |  |  |  | 1
7(10/25-10/31) | 4 | 2 | 2 |  | 1 | 0.5 | 0.5 |  |  | 1
8(11/1-11/7) | 10 | 4 | 6 |  | 2 |  | 1 | 1 |  | 1
9(11/8-11/14) | 9 | 7 | 2 |  | 2 | 1 | 2 | 2 |  | 1
10(11/15-11/21) | 10 | 5 | 5 |  | 2 |  | 1 | 2 |  | 1
11(11/22-11/28) | 9 | 4 | 5 |  | 2 |  | 1 | 1 |  | 1
12(11/29-12/5) | 12 | 7 | 5 |  | 2 |  | 2 | 2 | 1 | 1
13(12/6-12/12) | 6 | 1 | 5 |  |  |  | 1 |  |  | 0

## Yash Bavishi
CS673F16T1_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (09/19-09/26) | 4 | 3 | 1 | 0 - learning git, existing project 1 - discuss project idea 5 - team meeting | 2 | 1 |  |  |  | 1 |  | 0 - continue learning djano,python 1 - define project requirements 5 - team meeting | 6
3 (9/27-10/3) | 3 | 2 | 1 | 5 - team meeting 6 - working on SPPP | [5 empty] | 1 | 2 |  | 4
4 (10/4-10/10) | 3 | 2 | 1 | 5 - team meeting / task allotment 1 - Wrting User stories |  | 2 |  |  |  | 1
5 (10/11-10/17) | 3 | 3 | 1 |  | 2 | 1
6 (10/18-10/24) | 5 | 4 | 1 |  | 4 |  |  |  |  | 1
7(10/25-10/31) | 3 | 2 | 1 |  | 2 |  |  |  |  | 1
8(11/1-11/7) | 10 | 3 | 1 |  | 6 |  | 1 | 3 |  | 0
9(11/8-11/14) | 8 | 3 | 1 |  |  |  |  | 6 | 1 | 1
10(11/15-11/21) | 5 | 3 | 1 |  | 1 |  |  | 3 |  | 1
11(11/22-11/28) | 5 | 4 | 1 |  |  |  |  | 4 |  | 1
12(11/29-12/5) | 7 | 2 | 1 |  |  |  |  | 6 |  | 1
13(12/6-12/12) | 7 | 2 | 1 |  |  |  |  | 6 |  | 1

## Kevin Ding
CS673F16T1_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (09/19-09/26) | 3 | 2 | 1 |  | 2 | 1
3 (9/27-10/3) | 3 | 2 | 1 |  | 1.5 | 1.5
4 (10/4-10/10) | 4 | 2 | 2 |  | 2 | 2
5 (10/11-10/17) | 3 | 2 | 1 |  | 2 | 1
6 (10/18-10/24) | 3 | 2 | 1 |  | 2 | 1
7(10/25-10/31) | 4 | 2 | 2 |  | 2 | 2
8(11/1-11/7) | 10 | 8 | 2 |  | 3 |  | 2 | 3 | 1 | 1
9(11/8-11/14) | 12 | 7 | 5 |  | 3 |  |  | 4 | 1 | 4
10(11/15-11/21) | 5 | 5 | 0 |  | 1 |  | 2 | 2
11(11/22-11/28) | 5 | 5 | 0 |  | 1 |  | 1 | 2 | 1
12(11/29-12/5) | 12 | 10 | 2 |  | 3 |  | 2 | 3 | 2 | 2
13(12/6-12/12) | 11 | 5 | 5 |  |  |  |  | 1 | 2 | 5 | 3

## Bakyt Bakayeva
CS673F16T1_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (09/19-09/26)
3 (9/27-10/3)
4 (10/4-10/10)
5 (10/11-10/17)
6 (10/18-10/24)
7(10/25-10/31)
8(11/1-11/7)
9(11/8-11/14)
10(11/15-11/21)
11(11/22-11/28)
12(11/29-12/5)
13(12/6-12/12)

## Kevin Sperling
CS673F16T1_weeklyreport
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
2 (09/19-09/26) | 2.5 | 1.5 | 1 |  | 1 | 0.5 | 0 | 0 | 0 | 1 | 0 | 3 | 5
3 (9/27-10/3) | 5 | 4 | 1 |  | 2 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 5
4 (10/4-10/10) | 6 | 5 | 1 |  | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 3 | 5
5 (10/11-10/17) | 2 | 2 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 5
6 (10/18-10/24) | 3 | 2 | 1 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 5
7(10/25-10/31) | 4 | 3 | 1 |  | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 5
8(11/1-11/7) | 4 | 3 | 1 |  | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 5
9(11/8-11/14) | 5 | 4 | 1 |  | 1 | 0 | 0 | 3.5 | 0.5 | 0 | 0 | 3 | 5
10(11/15-11/21) | 3 | 3 | 0 |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 3
11(11/22-11/28) | 3 | 3 | 0 |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 3
12(11/29-12/5) | 8 | 7.5 | 0.5 |  | 0 | 0 | 0 | 7.5 | 0 | 0.5 | 0 | 3 | 8
13(12/6-12/12) | 19 | 14 | 5 |  | 0 | 0 | 0 | 14 | 0 | 2 | 0 | 0 | 0

## Totals
Weeks | Total Individual work time | Total meeting time | Learning | Requirement Analysis | Design | Implementation | Testing | Communication | Unclassified | Estimated tasks for next week | Total estimated time
2 (09/19-09/26) | 14.5 | 5.5 | 10 | 4.5 | 1 | 0 | 0 | 5 | 0 | 5 | 24
3 (9/27-10/3) | 19 | 5.5 | 7.5 | 4.5 | 2 | 1 | 1 | 3 | 4 | 5 | 24
Iteration 0 Totals | 33.5 | 11 | 17.5 | 9 | 3 | 1 | 1 | 8 | 4 | 10 | 48
4 (10/4-10/10) | 20.5 | 7 | 5.5 | 8 | 4 | 2 | 1 | 4 | 1 | 6 | 16.5
5 (10/11-10/17) | 20 | 3.5 | 10 | 5 | 3 | 3 | 0 | 2 | 0 | 3 | 15
6 (10/18-10/24) | 22 | 5.5 | 11 | 1 | 4 | 5 | 1 | 4 | 0 | 3 | 13
Iteration 1 Totals | 62.5 | 16 | 26.5 | 14 | 11 | 10 | 2 | 10 | 1 | 12 | 44.5
7(10/25-10/31) | 20 | 8 | 8 | 5.5 | 3.5 | 4 | 1 | 4 | 0 | 3 | 15
8(11/1-11/7) | 29 | 11.5 | 15 | 1 | 7 | 12 | 2 | 4 | 0 | 3 | 19
9(11/8-11/14) | 32 | 10.5 | 9 | 2 | 3 | 20.5 | 3.5 | 8 | 0 | 3 | 19
Iteration 2 Totals | 81 | 30 | 32 | 8.5 | 13.5 | 36.5 | 6.5 | 16 | 0 | 9 | 53
10(11/15-11/21) | 28 | 7.5 | 10 | 0 | 7 | 11 | 1 | 4 | 0 | 3 | 19
11(11/22-11/28) | 25 | 8 | 5 | 0 | 5 | 13 | 2 | 5 | 0 | 3 | 19
12(11/29-12/5) | 38.5 | 12.5 | 6 | 1 | 7 | 24.5 | 6 | 6.5 | 0 | 3 | 24
12(12/6-12/12) | 32 | 23 | 1 | 0 | 3 | 27 | 5 | 12 | 3 | 0 | 8
Iteration 3 Totals | 123.5 | 51 | 22 | 1 | 22 | 75.5 | 14 | 27.5 | 3 | 9 | 70
Total Project Time | 300.5

## Graph
Weeks | Meeting time | Learning | Requirement Analysis | Design | Implementation | Testing | Communication | Unclassified | Estimated tasks for next week | Total estimated time | Total Individual work time
09/19-09/26 | 5.5 | 10 | 4.5 | 1 | 0 | 0 | 5 | 0 | 5 | 24 | 14.5
9/27-10/3 | 5.5 | 7.5 | 4.5 | 2 | 1 | 1 | 3 | 4 | 5 | 24 | 19
10/4-10/10 | 7 | 5.5 | 8 | 4 | 2 | 1 | 4 | 1 | 6 | 16.5 | 20.5
10/11-10/17 | 3.5 | 10 | 5 | 3 | 3 | 0 | 2 | 0 | 3 | 15 | 20
10/18-10/24 | 5.5 | 11 | 1 | 4 | 5 | 1 | 4 | 0 | 3 | 13 | 22
10/25-10/31 | 8 | 8 | 5.5 | 3.5 | 4 | 1 | 4 | 0 | 3 | 15 | 20
11/1-11/7 | 11.5 | 15 | 1 | 7 | 12 | 2 | 4 | 0 | 3 | 19 | 29
11/8-11/14 | 10.5 | 9 | 2 | 3 | 20.5 | 3.5 | 8 | 0 | 3 | 19 | 32
11/15-11/21 | 7.5 | 10 | 0 | 7 | 11 | 1 | 4 | 0 | 3 | 19 | 28
11/22-11/28 | 8 | 5 | 0 | 5 | 13 | 2 | 5 | 0 | 3 | 19 | 25
11/29-12/5 | 12.5 | 6 | 1 | 7 | 24.5 | 6 | 6.5 | 0 | 3 | 24 | 38.5
12/6-12/12 | 23 | 1 | 0 | 3 | 27 | 5 | 12 | 3 | 0 | 8 | 32